Alpha v0.1 – May 31st
Basic UI, character can move, working db, several images uploaded
Alpha v0.2 – June 7th
Add testings suite for all prior code, fix bugs in v0.1
+10 more graphics, worldbuilder 50% done
Alpha v0.3 – June 14th
Fix bugs found in v0.2, +10 more graphics, finished worldbuilder,
Add support for game controllers, Begin working on story
Alpha v0.4 – June 21st
Fix bugs found in v0.3, +10 graphics, continue story, construct
Game mechanics inheritance tree.
Alpha v0.5 -June 28th
Fix bugs found in v0.4, continue story, +10 graphics, 50% random
Map generation tool.
Alpha v0.6 – July 1st
Fix bugs found in v0.5, +10 graphics, finish random map generator
Tool.
Alpha v0.7 July 7th
Fix bugs found in v0.6, complete story outline for the game,
+10 graphics, create a plan for moving the db to a remote system
Alpha v0.8 – July 14th
Fix bugs found in v0.7, +10 graphics for the game, begin
Implementing remote db for multiplayer.
Alpha v0.9 – July 20th
Fix bugs in v0.9, get game sounds and implement them,
Add multiplayer pvp mode (1st multiplayer game mode)
Alpha v1.0 – July 25th
Fix bugs in 0.9 and polish overall game. Should be releasable for
A game in alpha.